## PAPER TEMPLATE
milestone | Owner | start date | due date | status | notes

## Staff
Name | Role | Primary responsibilities | FTE | Org | Not started
Ellie B. | Project Manager | Supporting creation of database library; supporting publications processes | 5% | SORCE | On track
Tom C. | Analyst | Advising and executing analysis plans; leading the creation of relevant processes and forms for project intake | 30% | SORCE | Delayed
Becky S. | Analyst | Managing creation of database library; supporting creation of project intake processes and forms | 20% | SORCE | Complete
Erika W. | SORCE Executive Director | Overseeing all Ortho partnership activities; advising on publications | 2% | SORCE
Amy Cizik | PI, Ortho Partnership Lead |  | 0% | Ortho
Debbie Bratt | Ortho Project Manager |  | 0% | Ortho
Kelsey Pullar | SORCE Project Manager |  | 0% | SORCE
Stephanie Benipal | SORCE Project Coordinator |  | 0% | SORCE
Jeanette Yang | SORCE Project Coordinator |  | 0% | SORCE
Matthew Thompson | PI |  | 0% | Ortho

## All
project | PI | Name | Owner | CurrentPhase | ProjectDescription | StartDate | EndDate | Type | AmyRole
1 | All | Department Funds | All |  | Misc | 2018-07-01 | 2018-12-31 | Department Partnership | Lead
2 | Sports Med | ACL delay paper | Kweon | On track | ACL Aim 1: delay; Marketscan cohort | 2018-04-01 | 2018-08-01 | Publication | Collaborator
3 | Sports Med | ACL Cost paper | Kweon | On track | ACL Aim 2: cost/utilization; Marketscan cohort | 2018-07-01 | 2018-09-01 | Publication | Collaborator
4 | Sports Med | MarketScan - joint 2 | Hagen | On track | A TBD paper on TBD joint, using MarketScan data | 2018-09-01 | 2018-12-31 | Publication | Collaborator
5 | Ortho | Resident support | SORCE - Tom | On track | Creation of infrastructure needed for residents and fellows to implement research projects at SORCE | 2018-07-01 | 2018-11-30 | Research infrastructure | Collaborator
6 | Ortho | MarketScan toolkit | SORCE - Tom | On track | Creation of toolkit to support efficient planning and execution of MarketScan projects at SORCE | 2018-07-01 | 2018-12-31 | Data management | Collaborator
7 | Ortho | Ortho dataset library | SORCE - Becky | On track | Organizing and creating documentation to support the sustainable maintenance of an orthopedica dataset library at SORCE | 2018-07-01 | 2018-12-31 | Research infrastructure | Collaborator

## Pubs
Division | Target date | Topic | Journal | Lead Author | Phase | Title
Sports Med | Mid-August 2018 | ACL Delay | American Journal of Sports Medicine | C. Kweon | Submitted to journal | Factors Associated with Diagnosis, Treatment, and Healthcare Utilization of Acute ACL Injuries
Sports Med | End January 2019 | ACL Cost | TBD | C. Kweon | Defining cohort | TBD
Sports Med | February 2019 | MarketScan: hip | TBD | M. Hagen | Defining cohort | TBD
Residents | Summer 2019 | MarketScan: hand | TBD | S. Chawla | Research question development | TBD

## 2.ACL delay paper
milestone | owner | start | end | status | notes | TARGET SUBMISSION DATE | 9/28/18
Review final analysis | Author team | 2018-05-01 | 2018-07-01 | On track
Identify target journal | Lead author | 2018-07-01 |  | Complete | AJSM
Pull manuscript requirements from target journal | Project manager | 2018-08-01 |  | Not started
Proofread, finalize references | Project manager | 2018-08-07 |  | Not started
Revise nearly-final draft | Lead author | 2018-07-01 | 2018-07-31 | Not started
Circulate final draft of paper | Lead author | 2018-08-01 | 2018-08-07 | Not started
Submit to AJSM | Project manager | 2018-08-15 |  | Not started

## 3.ACL Cost paper
milestone | owner | start | end | status | notes | TARGET SUBMISSION DATE | 2019-01-31
Identify authorship team | Analyst | 2018-07-01 | 2018-07-15 | Not started
Complete intake process for project with analyst team | Lead author | 2018-07-15 | 2018-08-15 | Not started
Identify target journal | Lead author | 2018-11-01 |  | Not started
Draft analysis plan | Analyst | 2018-08-15 | 2018-09-15 | Not started
Draft intro + background section | Lead author | 2018-11-08 | 2018-11-15 | Not started
Review and edit analysis plan | Author team | 2018-11-15 | 2018-11-22 | Not started
Adjust analysis plan | Analyst | 2018-11-22 | 2018-11-29 | Not started
Approve analysis plan | Lead author | 2018-11-29 |  | Not started
Draft dummy tables; review with analyst | Author team | 2018-11-15 | 2018-11-29 | Not started
Draft methods section | Analyst | 2018-11-22 | 2018-12-06 | Not started
Complete first round of analysis | Analyst | 2018-11-29 | 2018-12-13 | Not started
Review completed dummy tables | Author team | 2018-12-13 |  | Not started
Complete any revised analyses | Analyst | 2018-12-20 | 2019-01-03 | Not started
Adjust and review updated analysis | Author team | 2019-01-03 |  | Not started
Draft results section | Lead author | 2018-12-27 | 2019-01-03 | Not started
Draft conclusions section | Lead author | 2019-01-03 | 2019-01-10 | Not started
Finalize and circulate first draft of paper | Lead author | 2019-01-10 |  | Not started
Refine first draft | Author team | 2019-01-31 | 2019-02-07 | Not started
Revise and circulate final draft of paper | Lead author | 2019-01-24 |  | Not started
Proofread, finalize references | Project manager | 2019-01-24 | 2019-01-31 | Not started
Submit paper | Project manager | 2019-01-31 |  | Not started
Formulas:
end = WORKDAY([end, row below],-5)
end = WORKDAY(Table711[[#This Row],[start]],5)

## 4.MarketScan - joint 2
milestone | owner | start | end | status | notes | TARGET SUBMISSION DATE | 2018-11-30
Identify supporting clinician to define cohort | Analyst | 2018-07-02 | 2018-07-13 | In progress
Identify authorship team | Analyst | 2018-09-07 |  | Not started
Complete intake process for project with analyst team | Lead author | 2018-08-10 | 2018-08-24 | Not started
Identify target journal | Lead author | 2018-08-24 | 2018-08-31 | Not started
Draft analysis plan | Analyst | 2018-09-07 | 2018-09-14 | Not started
Draft intro + background section | Lead author | 2018-09-07 | 2018-09-14 | Not started
Review and edit analysis plan | Author team | 2018-09-14 | 2018-09-21 | Not started
Adjust analysis plan | Analyst | 2018-09-21 | 2018-09-28 | Not started
Approve analysis plan | Lead author | 2018-09-21 | 2018-09-28 | Not started
Draft dummy tables; review with analyst | Author team | 2018-09-14 | 2018-09-28 | Not started
Draft methods section | Analyst | 2018-09-21 | 2018-10-05 | Not started
Complete first round of analysis | Analyst | 2018-09-28 | 2018-10-12 | Not started
Review completed dummy tables | Author team | 2018-10-05 | 2018-10-12 | Not started
Complete any revised analyses | Analyst | 2018-10-19 | 2018-11-02 | Not started
Adjust and review updated analysis | Author team | 2018-10-26 | 2018-11-02 | Not started
Draft results section | Lead author | 2018-10-05 | 2018-11-02 | Not started
Draft conclusions section | Lead author | 2018-11-02 | 2018-11-09 | Not started
Finalize and circulate first draft of paper | Lead author | 2018-11-02 | 2018-11-09 | Not started
Refine first draft | Author team | 2018-11-09 | 2018-11-16 | Not started
Revise and circulate final draft of paper | Lead author | 2018-11-16 | 2018-11-23 | Not started
Proofread, finalize references | Project manager | 2018-11-23 | 2018-11-30 | Not started
Submit paper | Project manager | 2018-11-23 | 2018-11-30 | Not started
Formulas:
start = WORKDAY([end, row below], -25)
end = WORKDAY([end, row below],-5)

## 5.Residentsupport
milestone | owner | start | end | completion date | status | notes

## 6.Ortho dataset library
Dataset | Task | Owner | Due | Status | notes
1. National Inpatient Sample | Transfer data to Becky | Amy | 2018-09-07 | On track
1. National Inpatient Sample | Add Becky to DUA | Ellie | 2018-09-07 | Not started
1. National Inpatient Sample | Create structure, access policy, and maintenance plan for database | Becky | 2018-09-28 | Not started
1. National Inpatient Sample | Database is complete, accessible by ortho collaborators, per SORCE policy | Becky | 2018-09-30 | Not started
2. NY State Ambulatory Surgery and Services Databases | Set-up meeting with Jerry Huang | Amy | 2018-08-31 | On track
2. NY State Ambulatory Surgery and Services Databases | Transfer data to Becky | Amy | 2018-09-14 | Not started
2. NY State Ambulatory Surgery and Services Databases | Create structure, access policy, and maintenance plan for database | Becky | 2018-10-26 | Not started
2. NY State Ambulatory Surgery and Services Databases | Database is complete, accessible by ortho collaborators, per SORCE policy | Becky | 2018-10-31 | Not started
3. National Trauma Data Bank | Finalize plan for payment between collaborators | Ellie | 2018-08-31 | On track
3. National Trauma Data Bank | Draft application on behalf of collaborators | Amy | 2018-09-14 | On track
3. National Trauma Data Bank | Submit application to NTDB | Ellie | 2018-09-21 | Not started
3. National Trauma Data Bank | Application under review | n/a | 2018-11-01 | Not started
3. National Trauma Data Bank | Transfer data to Becky | Ellie | 2018-11-01 | Not started
3. National Trauma Data Bank | Create structure, access policy, and maintenance plan for database | Becky | 2018-12-01 | Not started
3. National Trauma Data Bank | Database is complete, accessible by ortho collaborators, per SORCE policy | Becky | 2018-12-01 | Not started